## Sheet1
Sr.# | Case# | Practice code | Title | Assignee | TPM Priority | Requirement Status | PMO Remarks | Story Points | Module | Fixation Type | Aging | Complexity | PPt | Merging | Status | Resolution Date
1 | 552559843-S |  | BILLING DESK BOARD ISSUE | Hamza Zulfiqar | 1 | Yes |  | 4 | Dilling Desk | Bug | 6 | 3 |  |  | Done | 2022-11-19
2 | 552564551-S |  | Inconsistency in Dasbhoard pending Faxes | Hamza Zulfiqar | 2 | Yes |  | 4 | Dashboard Report | Bug | 1 | 3 |  |  | Done | 2022-11-19
3 | 552564892-S |  | Credentialing status report Client Phase I | Irfan Fazal | 1 | Yes |  | 4 | Credentialing Dashboard | Bug | 1 | 3 |  |  | Done | 2022-11-19
4 | 552564893-S |  | Credentialing status report API Phase I | Irfan Fazal | 1 | Yes |  | 4 | Credentialing Dashboard | Bug | 1 | 3 |  |  | Done | 2022-11-19
5 | 552569459-S |  | Credentialing status report API Phase II | Irfan Fazal | 1 | Yes |  | 2 | Credentialing Reports | New Request | 0 | 4 |  |  | Done | 2022-11-26
6 | 552569462-S |  | Credentialing status report Client Phase II | Irfan Fazal | 1 | Yes |  | 2 | Credentialing Reports | New Request | 0 | 4 |  |  | Done | 2022-11-26
7 | 552569469-S |  | Search Filter enhancements on CSR | Irfan Fazal | 2 | Yes |  | 2 | Credentialing Dashboard | Bug | 0 | 3 |  |  | Done | 2022-11-26
8 | 552569475-S |  | Export to excel enhancements on Credentialing status reports | Irfan Fazal | 2 | Yes |  | 2 | Credentialing Dashboard | Bug | 0 | 3 |  |  | Done | 2022-11-26
9 | 552569463-S |  | CAQH Report Changes Client Side | Hamza Zulfiqar | 2 | Yes |  | 2 | Credentialing Dashboard | New Request | 0 | 4 |  |  | Done | 2022-11-26
10 | 552569456-S |  | API Side CAQH Report Changes | Hamza Zulfiqar | 2 | Yes |  | 2 | Credentialing Dashboard | New Request | 0 | 4 |  |  | Done | 2022-11-26
11 | 552569466-S |  | Export to Excel inconsistency in CAQH Report Changes | Hamza Zulfiqar | 2 | Yes |  | 2 | Credentialing Dashboard | Bug | 0 | 3 |  |  | Done | 2022-11-26
12 | 552569471-S |  | CAQH Report Changes Smart search filter inconsistency | Hamza Zulfiqar | 2 | Yes |  | 2 | Credentialing Dashboard | Bug | 0 | 3 |  |  | Done | 2022-11-26
13 | 552574041-S |  | PTL ON WEB CHANGES | Irfan Fazal | 1 | Yes |  | 2 | CLAIMS | New Request | 0 | 4 |  |  | Done | 2022-12-03
14 | 552574108-S |  | APPEAL REQUIRED ON DASHBOARD | Irfan Fazal | 1 | Yes |  | 2 | BILLING DESK | Bug | 0 | 3 |  |  | Done | 2022-12-03
15 | 552574109-S |  | APPEAL REJECTED ON DASHBOARD | Irfan Fazal | 2 | Yes |  | 2 | BILLING DESK | Bug | 0 | 3 |  |  | Done | 2022-12-03
16 | 552574131-S |  | ERA Setup Changes Phase I | Hamza Zulfiqar | 1 | Yes |  | 3 | BILLING DESK | New Request | 0 | 4 |  |  | Done | 2022-12-03
17 | 552574135-S |  | API side ERA Setup Changes | Hamza Zulfiqar | 1 | Yes |  | 3 | BILLING DESK | New Request | 0 | 4 |  |  | Done | 2022-12-03
18 | 552575825-S |  | Need to update the Name Expiry Date to Revalidation Date | Irfan Fazal | 1 | Yes |  | 4 | Credentialing Dashboard | New Request | 0 | 4 |  |  | Done | 2022-12-04
19 | 552578186-S |  | Enhancements in appeal in review Billing desk. | Irfan Fazal | 1 | Yes |  | 2 | Billing Desk |  | 0 | 4 |  |  | Done | 2022-12-10
20 | 552578163-S |  | Add Enhancement filters in appeal dashboard | Irfan Fazal | 1 | Yes |  | 2 | Billing Desk |  | 0 | 4 |  |  | Done | 2022-12-10
21 | 552578149-S |  | Search enhancement for PPP Nasd | Irfan Fazal | 1 | Yes |  | 3 | PPP Nasd | New Request | 0 | 4 |  |  | Done | 2022-12-10
22 | 552578162-S |  | API SIDE ERA SETUP CHANGES Phase II | Hamza Zulfiqar | 1 | Yes |  | 3 | Credentialing Dashboard | New Request | 0 | 4 |  |  | Done | 2022-12-10
23 | 552578168-S |  | CLIENT SIDE ERA Setup Changes Phase II | Hamza Zulfiqar | 2 | Yes |  | 4 | Credentialing Dashboard | New Request | 0 | 4 |  |  | Done | 2022-12-11
24 | 552583210-S |  | Need to add modifier on ERA report | Irfan Fazal | 1 | Yes |  | 2 | Billing Claim | Service Request | 0 | 4 | yes |  | Done | 2022-12-17
25 | 552583212-S |  | Need to add Search filter enhancements on Dasbhoard report widget | Irfan Fazal | 1 | Yes |  | 2 | Billing Dashboard | Fixations | 0 | 3 | yes |  | Done | 2022-12-17
26 | 552580165-S |  | Need correct Statement | Irfan Fazal | 1 | Yes |  | 3 | Demographics | Fixations | 0 | 3 | yes |  | Done | 2022-12-17
27 | 552583199-S |  | SSCM Changes Client Side Phase I | Hamza Zulfiqar | 1 | Yes |  | 4 | SSCM | Service Request | 0 | 4 | yes |  | Done | 2022-12-17
28 | 552583213-S |  | API Side SSCM Changes Phase I | Hamza Zulfiqar | 2 | Yes |  | 4 | SSCM | Service Request | 0 | 4 | yes |  | Done | 2022-12-17
29 | 552583223-S |  | ERA Setup Enhancements | Hamza Zulfiqar | 2 | Yes |  | 4 | Billing Desk | Service Request | 0 | 4 | yes |  | Done | 2022-12-17
30 | 52584446-S |  | Decimal values issue | Irfan Fazal | 1 | Yes |  | 2 | NDC setup | Fixations | 1 | 4 | yes |  | Done | 2022-12-17
31 | 552588004-S |  | Crdentialing Revalidation Report API Phase 1 | Irfan Fazal | 1 | Yes |  | 2 | Credentialing Dashboard | Service Request | 0 | 4 | yes |  | Done | 2022-12-24
32 | 552588007-S |  | Crdentialing Revalidation Report Client Phase 1 | Irfan Fazal | 1 | Yes |  | 2 | Credentialing Dashboard | Service Request | 0 | 4 | yes |  | Done | 2022-12-24
33 | 552588008-S |  | Enhancements on Credentailing Revalidation Report | Irfan Fazal | 1 | Yes |  | 3 | Credentialing Dashboard | Service Request | 0 | 3 | yes |  | Done | 2022-12-24
34 | 552588290-S |  | Changes in Patient Statement View | Hamza Zulfiqar | 1 | Yes |  | 3 | Patient Statement | Enhancement | 0 | 3 | yes |  | Done | 2022-12-24
35 | 552588304-S |  | Enhancement in Export functionality. | Hamza Zulfiqar | 2 | Yes |  | 3 | Billing Desk | Enhancement | 0 | 3 | No |  | Done | 2022-12-24
36 | 552589405-S |  | Practice Filter not working correctly | Irfan Fazal | 3 | Yes |  | 2 | SSCM | BUG | 0 | 3 | No |  | Done | 2022-12-24
37 | 552593074-S |  | Crdentialing Revalidation Report API Phase II | Irfan Fazal | 1 | Yes |  | 2 | Credentialing Dashboard | Service Request | 0 | 4 | yes |  | Done | 2022-12-31
38 | 552593075-S |  | Crdentialing Revalidation Report Client Phase II | Irfan Fazal | 1 | Yes |  | 2 | Credentialing Dashboard | Service Request | 0 | 4 | yes |  | Done | 2022-12-31
39 | 552593079-S |  | Implement fitler and export consistency on Credentailing Revalidation Report Phase II | Irfan Fazal | 1 | Yes |  | 3 | Credentialing Dashboard | Service Request | 0 | 3 | yes |  | Done | 2022-12-31
40 | 552593214-S |  | Need to correct Remit Address on Patient Statement | Hamza Zulfiqar | 1 | Yes |  | 3 | Patient Demographics | Service Request | 0 | 3 | yes |  | Done | 2022-12-31
41 | 552593223-S |  | Unreconciled Deposit Slip Enhancements | Hamza Zulfiqar | 2 | Yes |  | 2 | Billing Desk | Incident | 0 | 3 | No |  | Done | 2022-12-31
42 | 552594276-S |  | TASK SCHEDULER ISSUE | Irfan Fazal | 1 | Yes |  | 2 | Task Schedular | Service Request | 0 | 4 | yes |  | Done | 2023-01-07
43 | 552597476-S |  | Change address on claim submission history | Irfan Fazal | 1 | Yes |  | 2 | Claims | Incident | 0 | 4 | yes |  | Done | 2023-01-07
44 | 552597484-S |  | Submission history address changed API | Irfan Fazal | 1 | Yes |  | 3 | Claims | Incident | 0 | 3 | yes |  | Done | 2023-01-07
45 | 552597427-S |  | Need to add user ID in SSCM | Hamza Zulfiqar | 1 | Yes |  | 3 | SSCM | Service Request | 0 | 3 | yes |  | Done | 2023-01-07
46 | 552591217-S |  | ADA AND TAR FORM ISSUE | Hamza Zulfiqar | 2 | Yes |  | 2 | Claims | Incident | 0 | 3 | No |  | Done | 2023-01-07
47 | 552601193-S |  | SUGGESTION REGARDING DP ISSUE. | Irfan Fazal | 1 | Yes |  | 3 | Carecloud Dayplanner | Service Request | 0 | 4 | no |  | Done | 2023-01-14
48 | 552602256-S |  | CARECLOUD DAYPLANNER ENHANCEMEnt | Irfan Fazal | 1 | Yes |  | 3 | Carecloud Dayplanner | Service Request | 0 | 4 | yes |  | Done | 2023-01-14
49 | 552602268-S |  | ENHANCEMENTS ON DAHBOARD REPORt | Irfan Fazal | 1 | Yes |  | 3 | Billing Desk | Service Request | 0 | 3 | yes |  | Done | 2023-01-14
50 | 552602277-S |  | Disable adjustment Reason in Claim Payment | Hamza Zulfiqar | 1 | Yes |  | 3 | SSCM | Service Request | 0 | 3 | yes |  | Done | 2023-01-14
51 | 552602290-S |  | Export and Smart search filter Enhancement | Hamza Zulfiqar | 1 | Yes |  | 3 | Billing Desk | Service Request | 0 | 3 | no |  | Done | 2023-01-14
52 | 552607716-S |  | Recertification Required Report changes | Irfan Fazal | 1 | Yes |  | 3 | Carecloud Dayplanner | Service Request | 0 | 4 | no |  | Done | 2023-01-21
53 | 552606910-S |  | NEED TO ADD MODIFIER IN THE SYSTEM | Irfan Fazal | 1 | Yes |  | 3 | Carecloud Dayplanner | Service Request | 0 | 4 | yes |  | Done | 2023-01-21
54 | 552607723-S |  | Credentialing Charges report enhancement | Hamza Zulfiqar | 1 | Yes |  | 3 | Credentialing Dashboard | Service Request | 0 | 3 | No |  | Done | 2023-01-21
55 | 552605487-S |  | NDC ISSUE | Hamza Zulfiqar | 1 | Yes |  | 3 | Billing Desk | Service Request | 0 | 3 | no |  | Done | 2023-01-21
56 | 552612723-S |  | Important Login changes on Nasd Automation client side | Irfan Fazal | 1 | Yes |  | 3 | Nasd Automation Setup | Service Request | 0 | 3 | Yes |  | Done | 2023-01-28
57 | 552612738-S |  | Dashboard report changes Enhancements | Irfan Fazal | 2 | Yes |  | 3 | Billing Desk | Service Request | 0 | 2 |  |  | Done | 2023-01-28
58 | 552612727-S |  | Nasd Automation filelds addition | Irfan Fazal | 1 | Yes |  | 3 | Nasd Automation Setup | Service Request | 0 | 3 | yes |  | Done | 2023-01-28
59 | 552612626-S |  | Addition of Rectified case type | Hamza Zulfiqar | 1 | Yes |  | 3 | SSCM module | Service Request | 0 | 4 | Yes |  | Done | 2023-01-28
60 | 552612652-S |  | Update practice Code to Mandatory Field | Hamza Zulfiqar | 1 | Yes |  | 3 | Billing Desk | Service Request | 0 | 4 | Yes |  | Done | 2023-01-28
61 | 552617922-S |  | Statement Time Period | Irfan Fazal | 2 | Yes |  | 3 | Practice Provider Profile(Nasd) | Service Request | 0 | 3 | Yes |  | Done | 2023-02-04
62 | 524394743-S |  | Sent Appeals Follow-Up-Alias need to be updated | Irfan Fazal | 2 | Yes |  | 3 | Auto Job(Sent Appeal follow up) | Service Request | 0 | 3 | No |  | Done | 2023-02-04
63 | 552616966-S |  | QA Executive is unable to access highlighted box | Irfan Fazal | 1 | Yes |  | 3 | Call QA module | Service Request | 0 | 3 | No |  | Done | 2023-02-04
64 | 552608813-S |  | Need to fix ( Caller Comments issue ) | Hamza Zulfiqar | 1 | Yes |  | 3 | Calling Module | Bug | 0 | 4 | No |  | Done | 2023-02-04
65 | 552618010-S |  | Need to correct Remit Address request | Hamza Zulfiqar | 1 | Yes |  | 3 | Patient Demographics | Service Request | 0 | 4 | Yes |  | Done | 2023-02-04
66 | 552617861-S |  | SPEACIALL PROJECT ISSUE | Irfan Fazal | 2 | Yes |  | 3 | DayPlanner | Bug | 9 | 2 | No |  | Resolved | 2023-02-11
67 | 552621398-S |  | PATIENT DEU (DUE) | Irfan Fazal | 3 | Yes |  | 3 | Claiims | Bug | 4 | 3 | No |  | Resolved | 2023-02-11
68 | 552620576-S |  | ASSISTANCE REQUIRED | Hamza Zulfiqar | 1 | Yes |  | 3 | Claims | Service Request | 5 | 3 | No |  | Resolved | 2023-02-11
69 | 552622870-S | 1010835 | FINANCIAL SUMMARY | Hamza Zulfiqar | 3 | Yes |  | 3 | Reports | Bug | 2 | 3 | No |  | Resolved | 2023-02-11
70 | 552624394-S |  | Enhancement in Application Tracking Report | Hamza Zulfiqar | 3 | Yes |  | 3 | Credentialing Dashboard | Service Request | 0 | 3 | No |  | Resolved | 2023-02-11
71 | 552628490-S |  | EMILIE KOSAKOWSKI ACC 004387133 | Irfan Fazal | 1 | Yes |  | 3 | APPEALS | Bug | 9 | 2 | No |  | In-Progress | 2023-02-18
72 | 552628701-S |  | Note check on Claim level client | Irfan Fazal | 2 | Yes |  | 3 | Claims | Service Request | 4 | 3 | YES |  | In-Progress | 2023-02-18
73 | 552628703-S |  | Note mandatory check funcationality API | Irfan Fazal | 2 | Yes |  | 3 | Claims | Service Request | 5 | 3 | YES |  | In-Progress | 2023-02-18
74 | 552628839-S |  | Client Side Practice Assignment | Hamza Zulfiqar | 1 | Yes |  | 3 | Users Setup | Service Request | 0 | 3 | Yes |  | In-Progress | 2023-02-18
75 | 552628858-S |  | Permanent Practice Assignment API side | Hamza Zulfiqar | 1 | Yes |  | 3 | Users Setup | Service Request | 0 | 3 | Yes |  | In-Progress | 2023-02-18
76 | 552628873-S |  | User Profile Setup Enhancements | Hamza Zulfiqar | 1 | Yes |  | 3 | Users Setup | Service Request | 0 | 3 | No |  | In-Progress | 2023-02-18

## Sheet2
Branch-Name | JIRA ID | JIRA Description | Product | Stored Procedure Details/Tables
MTBCITSP2-4914 | MTBCITSP2-4914 | 552612723-S,Important Login changes on Nasd Automation | SECURESOFT | WEBSOFT_GET_NASD_IMPORTANT_LOGINS_V2(FOX_UAT)
MTBCITSP2-4902 | MTBCITSP2-4902 | Patient statement address changed on RCM | SECURERCM
MTBCITSP2-4956 | MTBCITSP2-4956 | 552608813-S ,Need to fix ( Caller Comments issue ) | SECURESOFT
MTBCITSP2-4755 | MTBCITSP2-4755 | 552618010-S,Need to correct Remit Address request |  | AF_PROC_PatientStatement_Enhancedview_V4(FOX_UAT)
MTBCITSP2-4953 | MTBCITSP2-4953 | 552617922-S,Statement Time Period | SECURESOFT | MTBCSOFT_WEB_PRACTICE_PATIENT_BILLING_V4 (FOX_UAT)
ALTER TABLE PRACTICES
ADD STATEMENT_TIME_PERIOD VARCHAR(3) NULL ( FOX_UAT)
WEBSOFT_SET_PRACTICE_V2 (FOX_UAT)
MTBCITSP2-5011 | MTBCITSP2-4995 | 552624394-S Enhancement in Application Tracking Report | SECURESOFT
MTBCITSP2-5011 | MTBCITSP2-5011 | 552620576-S,ASSISTANCE REQUIRED | SECURESOFT
MTBCITSP2-4670 | MTBCITSP2-4670 | Need to add modifier on ERA report | securesoft | MTBCSOFT_WEB_PROC_LEVEL_PAYMENT_DETAIL_V3
MTBCITSP2-4691 | MTBCITSP2-4628 | Search enhancement for PPP Nasd | securesoft
MTBCITSP2-4721 | MTBCITSP2-4721 | Changes in Patient Statement View | securesoft
MTBCITSP2-4691 | MTBCITSP2-4691 | Practice Filter not working correctly(SSCM) | securesoft | MTBCSOFT_WEB_CASE_STATUS_PROGRESS_WITHOUT_DOCUMENT_ALL_CASE_V14
MTBCITSP2-4755 | MTBCITSP2-4755 | NEED TO CORRECT REMIT ADDRESS | securesoft | AF_PROC_PatientStatement_Enhancedview_V3
MTBCITSP2-4814 | MTBCITSP2-4814 | SUGGESTION REGARDING DP ISSUE | securesoft | MTBC_SOFT_GET_CARECLOUD_EXCEPTION_ALL_V2
MTBCITSP2-4795 | MTBCITSP2-4795 | TASK SCHEDULER ISSUE | securesoft
MTBCITSP2-4797 | MTBCITSP2-4797 | Need to add user ID in SSCM(only SP updated) | securesoft | MTBCSOFT_WEB_CASE_STATUS_PROGRESS_WITHOUT_DOCUMENT_ALL_CASE_V14
MTBCITSP2-4719 | MTBCITSP2-4719 | Credentialing Revalidation Report | securesoft | WEBSOFT_CREDENTIAL_REVALIDATION_REPORT
WEBSOFT_GET_CRED_PAYERS_VI
WEBSOFT_GET_CREDENTIALING_ASSIGNEE_V1
MTBCITSP2-4826 | MTBCITSP2-4826 | Disable adjustment Reason in Claim Payment | securesoft | ALTER TABLE mis_tbl_fillcombo ADD [Disabled] BIT NULL;
update mis_tbl_fillcombo set Disabled=1 where saved_value='Adjusted as per practice special instructions'
MTBCSOFT_WEB_GET_ADJUSTMENT_REASONS_V1
MTBCITSP2-4874 | MTBCITSP2-4874 | NEED TO ADD MODIFIER IN THE SYSTEM and Recertification Change report of dashboard | securesoft
MTBCITSP2-4408 | NEED TO FIX ISSUE | securesoft | MTBCITSP2-4408 | 11/07/2022-11/12/2022
MTBCITSP2-4465 | Credentialing status report | securesoft | MTBCITSP2-4465 | 11/21/2022-11/26/2022
MTBCITSP2-4531 | CAQH Report Changes | securesoft | MTBCITSP2-4531 | 11/21/2022-11/26/2022
MTBCITSP2-4579 | PTL ON WEB CHANGES | securesoft | MTBCITSP2-4579 | 11/28/2022-12/03/2022
MTBCITSP2-4465 | Need to update the Name Expiry Date to Revalidation Date | securesoft | MTBCITSP2-4465 | 11/28/2022-12/03/2022
MTBCITSP2-3733 | Enhancements on securesoft | securesoft | MTBCITSP2-3733 | 11/01/2022-12/03/2022